## Table 1
Revised 2/10/2023
TMDL Implementation Tracking Matrix: Aumsville, Oregon Compliance years 2018-2023
Aumsville has legal authority over land use on 730 acres within the City’s limits. Brought before city council October 22, 2018.
POLLUTANT What pollutants does the TMDL address? | SOURCE What sources of this pollutant are under your jurisdiction? | STRATEGY What is being done, or what will you do to reduce and/or control pollution emanating from this source? | HOW Specifically, how will this be done? | MEASURE How will you demonstrate successful implementation or completion of this strategy? | TIMELINE When will the strategy begin? Be completed? | BENCHMARK What intermediate goals will be achieved, and by when, to know progress is being made? | STATUS/GOALS MET
Temperature |  | Street tree program Trees to reduce street temperatures and cool storm water | Require street trees to be planted during new or redevelopment of properties. Enforce street tree ordinance Update development code to require street trees | Require review of development and require street trees to be included Track the number of trees planted | on-going |  | 2018-62 Street trees planted in new development 2019- 60 Street trees planted in new developments. 4 street trees planted in commercial zone. 2020- 74 Street trees planted, 18 in residential, 56 in the commercial zone. 2021- 1 street tree replaced. Contract with tree service to spray and fertilize. HP Civil project included 33 new street trees along Aumsville Hwy. and Olney St. 2022- 22 trees planted this year and we continue to maintain existing street trees by contracting fertilization and pest control along with pruning to promote healthy canopy growth.
| Solar radiation input | a. Maintain existing shading vegetation.  Most riparian area is already park area or open space. | Plan and fund plantings along waterways | Visually monitor waterway vegetation. Track the number of new plantings | on-going | Compare areas at five-year intervals to determine the state of and changes to riparian areas | 2018-Consulted MCSWC about planting trees along Highberger Ditch. This is an area that we are hav A hard time establishing tree 2019-planted 5 trees along Highberger ditch detention area to shade waterway. 2020- 450 trees planted in stormwater detention basins and ripairion areas. Many did not survive. 2021- replaced 8 trees around storm water detention basins. Started 20 willow trees to plant Along Highberger Ditch 2022- Planted trees in Highberger ditch detention ponds again, removed invasive blackberries along to creek to promote growth of the Red Twig Maples.
|  | b. Work Marion County Soil and Water Conservation Council to initiate riparian tree or other plantings. . | Contact MCSWC about plantings and strategies for Highberger Ditch | Monitor new growth in riparian areas and review annually | on-going | Establish a good working relationship with all parties involved At least one riparian tree planting completed every two years | 2018-MCSWC project along Mill Creek. Brush and debris cleaned up. Spray out weeds and Mow area in preparation of tree/brush planting. 2019- Planted 500 trees and 1400 willow and brushy plants along Mill Creek. City to maintain the MCSWC funded (grant) plantings for at least the next 5 years 2020- 350 trees planted in ripairian zone. 50 may have survived. 2021- No new projects this year. Continued to maintain project at Sewer reuse site. 2022- Continued maintenance of the sewer reuse site project, trees have seen good growth since the removeal of blackberries and overgrown brush.
Bacteria | Property owner yard debris next to waterways | Educate property owners to not dispose of their yard debris next to the waterway. | Public education in our monthly newsletter Update city code to include riparian zones and Illicit discharge ordinance Obtain access agreements with property owners to help maintain Highberger Ditch along Willamette St. | visual inspection of properties along water ways | On going | Property owners start clean up yard debris piles and move them farther away from the waterway | 2018-Planning for a community information event. Erosion and stream health. Special invites to Residents along waterways. City code is being updated this and the upcoming year. Requested that we include illicit discharge And riparian zone rules be implemented. 2019- codes are currently being rewritten and we have yet to review these new codes. 2020-City codes were updated. Still waiting for an illicit discharge code to be written. Newsletter Acticale to not dispose of debris along waterways. 2021-Talked with 6 residents about not dumping yard debris along Highberger Ditch 2022-Refer Mercury table.
| Catch basin | Clean catch basins at least once every two years | Public Works staff, Vactor truck | Track amount of material removed from catch basins | on-going | Less debris in storm lines | 2018-188 yards of material swept from the streets. 2019-272 yards of material have been swept from the streets. Only 1 yard of catch basin debris 2020-252 yards of material swept from streets, 6 yards of material cleaned from catch basins 2021-69 yards of material swept form streets,5 yards of material cleaned from catch basins 2022-Refer Mercury table.
| Street debris | Sweep street on a regular basis | Schedule monthly sweeping | Monitor debris on road surfaces | on-going | Cleaner streets and catch basins | 2018-The average street cleaning takes place 8 times a year. We are planning at least one sweeping A month, more as needed. 2019- Street sweeper was out sweeping 17 days 2020-Street sweeper was out sweeping 18 days this year 2021-Street sweeper swept the whole town 8 times this year. 2022-Refer Mercury table.
| Waste water treatment plant (monitoring indicates meets requirements) | Replace existing contact chamber for longer detention times and increase the bacterial kill before discharge. | Secure funding through rates and SDCs | Monitor as project continues | Continuing to still look for funding of the contact chamber. Construction to commence as soon as funding is available. Delayed due to funding | Loan funds secured Treatment plant constructed and operating Continue to meet discharge permit requirements | 2018-The wastewater plant is having a compliance problem with ammonia discharging into the creek. The city is now studying how to resolve this problem. 2019- WWTP now under a MAO to resolve the ammonia issue. 2020-Sewer Fascilties plan is underway. DEQ MAO to remove ammonia, sewer treatment enzyme Added to help improve treatment 2021- Facilties plan completed and submitted to DEQ, Additon of enzymes to the wastewater Seems to have improved the water quality being discharged. 2022-Secured funding for new wastewater treatment facility design and small amount toward construction. Moving the WWTP project forward is a priority of the City.
| Septic Systems | Development regulations state that all homes within the city, within 100 ft of sewer main shall connect to city sewer | Development regulations It is a requirement now and a condition of development approval. | Continued compliance | On-going | Short term: Heightened public awareness related to these issues Long term: | 2018-Worked with manufactured home park to eliminate sewer overflows there. They cleaned sewer Mainlines and repaired leaking manholes. 2019- One septic field has been abandoned, the property redeveloped and connected to city sewer 2020-One septic tank abandoned 2021- Two septic tanks abandoned in the old part of town.(church and gas station) 2022-Repaired 5 leaking manholes. Identified sewer lines running at capacity in Facilities plan and working to get these improvements included in the WWTP upgrades.
| Pet wastes | Prevent pet wastes from entering waterways | Install “Mutt Mitt” stations in parks with signs and waste cans Install in existing parks and install as new parks develop | Visual inspection of the park grounds Provide education/information in the monthly newsletter and web site | On going Assess additional stations where needed. | N/A | 2018-Keeping mutt-mitt stations filled with bags. 2019-Mutt Mitt stations are being well used. We have had to order many more bags than we have In the past. Not as many problems with pet waste in the park areas. 2020-Mutt Mitt stations are heavily used. Added additional mutt mitt station at Highberger Park 2021-New Mutt Mitt Station at Mill Ck Park and construct a new dog park additional garbage Receptacles. 2022-Recieved complaint about illegal pet waste dumping, was quickly investigated and resident cleaned up area where dumped. Let mobile home park know of pest waste being disposed of over a fence on City property they were informed anymore dumping would result in fines.
Enforce city ordinance to clean up after pets
| Sewer overflow | Eliminate sewage overflows or shorten event duration | Increase the cleaning schedule of sewer mains. 2012…City policy now to clean and TV sewer lines every 5 years. | Measurement of length of lines cleaned. Track number of overflow events | on going | Less sewage in streets, properties, and storm drains | 2018-Monitoring key manholes in sewer system. Doing more frequent cleaning of troublesome sewer Lines. 2019-Regular monitoring of manholes has kept pipe plugging from happening. New vacuum truck Was purchased and helps in cleaning sewer mains and cleaning catch basins 2020- We are now routinely cleaning areas that had been troublesome in the past. 1 minor sewer Back up due to grease. We were able to stop the back up before it reached the waterway. 2021- No sewer overflows. Constant monitoring catching problem areas before they happen. 2022-Cleaned several "problem" areas of the collection system before heavy rains to prevent overflows. No overflows this year.
| Complaints | Stop unwanted discharges to waterways, public education in city newsletter | Follow up on questions or complaints that involve drainage issues | Document and inform residents of water quality issues. Report to DEQ unauthorized discharges to waterways. | on-going | No unauthorized discharges | 2018-Received no complaints this year. Started a file to track information to citizens and training Attended. 2019- Only 3 complaints received were from neighbors complaining about water quality basins, Mainly the weeds growing along property lines. We took care of these right away. 2020- No complaints were received this year. Newsletter about dumping, storing, along waterway 2021- One resident cited for disposing dog waste in storm catchbasin. 2022-Refer Mercury table.
Mercury | Land development activities | Limit erosion to maintain clear, clean water | City has in the last year requested copies DEQ 1200c permits from developers and monitored their compliance | Public Works will monitor compliance with Land Development Regulations | on-going | Necessary erosion control barriers are installed. Track number of violations | 2018-New 1200c permit NW side of town. Contacted owner to clean street and not allow sediment Into our storm system 2019-monitored catch basins within new development area. Made sure erosion control stayed in Place and cleaned catchbasins. 2020-monitored catch basins in new subdivision. Cleaned if found there to be sediment accum Contactor was instructed to replace sediment control bags. 2021- Contactor installed water quality and detention basin, also installed a washrack for their trucks That sends catchbasin water from wash rack to wastewater treatment plant for processing. 2022-Refer Mercury table.
| Natural background in soil and rock | Limit erosion to maintain clear, clean water. | Identify areas of erosion | Public Works will monitor compliance with Land Development Regulations | On-going | One hundred percent compliance with code requirements. Track number of violations | 2018-New development has left bare ground. We made sure it was hydo-seeded. We monitored Run off from the area and had contractor add more sediment control. 2019-Had contractor reseed a portion of a development and install more erosion control 2020-contractor informed to replace sediment filter. Homeowner stopped from washing sediment Into catch basins. 2021-Construction at HP Civil site was monitoried for erosion by city staff, new ordenances put into Place to require additional landscaping when parking is installed. 2022-Refer Mercury table.
| Erosion and sedimentation runoff from residential, industrial, commercial properties | Limit erosion to maintain clear, clean water. Educate public thru monthly newsletter | City to enforce specific erosion control requirements (e.g. silt fences, mulching, seeding, avoid excavation during wet times) for new construction/reconstruction City to educate Public Works Staff on BMP’s | Track amount of material removed from catch basins. Check catch basins in construction areas to see if erosion control is effective Record of training | on-going When a training course is available | Catch basins don’t need to be cleaned as often and less sediment reaches the streams. Increased awareness when PW is out and about. | 2018-Home developers washing soil down the street. Having them clean streets, especially at the Bio-bags near catch basins. Attending trainings and passing along information to staff. Training file Has been started. 2019-Had 2 citizens moving debris out into the street and had them remove it. One was a lot of mud And they were not allowed to wash it down the drain. 2 employees attended erosion control training 2020-Overall contractors have been much better at providing erosion control measures. 2021-Residential properties have been landscaped, preventing erosion. A landscaping ordinance Was adopted to provide pervious areas do to addition to driveway areas. A street sweeper/ Wastewater dump pad was constructed to prevent washdown and materials from entering any Waterway. 2022-Refer Mercury table.